## Model reduction using Long Shor
WBS # | Name / Title | Type | Start Date | End Date | Estimated Hours | Actual Hours | Percent Complete | Resources | Predecessors | Notes | Comments | Task Color
1 | Model reduction using Long Short Term Memory neural networks | project | 2019-06-03 | 2019-09-05 | 0 | 0 | 18.42
1.1 | Wade | group | 2019-06-03 | 2019-09-05 | 0 | 0 | 18.42
1.1.1 | Train a simple LSTM network for square wave | task | 2019-06-03 | 2019-06-10 | 0 | 0 | 100 | WADE |  |  |  | blue2
1.1.2 | Training finish for square wave | milestone | 2019-06-10 | 2019-06-10 | 0 | 0 | 100 | WADE | 1.1.1 |  |  | blue2
1.1.3 | Test the perfomance of network | task | 2019-06-10 | 2019-06-17 | 0 | 0 | 100 | WADE | 1.1.2 |  |  | blue2
1.1.4 | Testing finish | milestone | 2019-06-17 | 2019-06-17 | 0 | 0 | 100 | WADE | 1.1.3 |  |  | blue2
1.1.5 | Make a detailed project plan | task | 2019-06-11 | 2019-06-24 | 0 | 0 | 50 | WADE |  |  |  | blue2
1.1.6 | Do some literature review for the project | task | 2019-06-11 | 2019-06-24 | 0 | 0 | 30 | WADE |  |  |  | blue2
1.1.7 | Submit the project plan | milestone | 2019-06-27 | 2019-06-27 | 0 | 0 | 0 | WADE | 1.1.6 |  |  | blue2
1.1.8 | Installing linux system for IC-Ferst | task | 2019-06-05 | 2019-06-12 | 0 | 0 | 100 | WADE |  |  |  | blue2
1.1.9 | Generate snapshots on IC-Ferst | task | 2019-06-28 | 2019-07-04 | 0 | 0 | 0 | WADE | 1.1.8 |  |  | blue2
1.1.10 | Generate ROM for snapshots(AE) | task | 2019-07-08 | 2019-07-19 | 0 | 0 | 0 | Gary | 1.1.9 |  |  | blue2
1.1.11 | Using LSTM network train a light version | task | 2019-07-08 | 2019-07-19 | 0 | 0 | 0 | WADE | 1.1.9 |  |  | blue2
1.1.12 | Model reduction | milestone | 2019-07-22 | 2019-07-22 | 0 | 0 | 0 | WADE, Gary | 1.1.10,1.1.11 |  |  | blue2
1.1.13 | Continuing read papers on LSTM and why GBR is used wider than LSTM | task | 2019-07-01 | 2019-07-19 | 0 | 0 | 0 | WADE |  |  |  | blue2
1.1.14 | Using LSTM to train the ROM and adjust the network to gain better performance | task | 2019-07-24 | 2019-08-01 | 0 | 0 | 0 | WADE | 1.1.12 |  |  | blue2
1.1.15 | Explore combining LSTM with domain decompsition | task | 2019-07-15 | 2019-08-01 | 0 | 0 | 0 | WADE |  |  |  | blue2
1.1.16 | Question? Any other jobs on LINUX? | task | 2019-06-18 | 2019-07-05 | 0 | 0 | 0 | WADE |  |  |  | red1
1.1.17 | Testing the performance on LSTM combining Domain docompsition | task | 2019-08-05 | 2019-08-22 | 0 | 0 | 0 | WADE | 1.1.14 |  |  | blue2
1.1.18 | Finish software part. | milestone | 2019-08-23 | 2019-08-23 | 0 | 0 | 0 | WADE | 1.1.17 |  |  | blue2
1.1.19 | Writing final report. | task | 2019-08-23 | 2019-09-05 | 0 | 0 | 0 | WADE |  |  |  | blue2
1.1.20 | Prepare final presentation | task | 2019-08-23 | 2019-09-05 | 0 | 0 | 0 | WADE |  |  |  | blue2